## Sheet1
Project Name | Project Number | Client Name | Start Date | Target Completion | Status | Contract Value | Total Budget | Materials Cost | Labor Cost | Subcontractor Cost | Other Costs | Total Costs | Gross Profit | Gross Margin % | Notes
Sample Residential Project | PRJ-2026-001 | John Smith | 2026-01-15 | 2026-04-15 | In Progress | 125000 | 100000 | 28500 | 32000 | 25000 | 8500 | 94000 | 31000 | 24.8% | On schedule
Sample Commercial Build | PRJ-2026-002 | ABC Company | 2026-02-01 | 2026-08-01 | In Progress | 450000 | 380000 | 95000 | 110000 | 85000 | 15000 | 305000 | 145000 | 32.2% | Waiting on permits
Sample Renovation | PRJ-2026-003 | Jane Doe | 2026-03-01 | 2026-05-15 | Not Started | 85000 | 72000 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Materials ordered
Sample Kitchen Remodel | PRJ-2025-045 | Bob Johnson | 2025-11-01 | 2026-01-15 | Completed | 65000 | 55000 | 18500 | 22000 | 8000 | 3500 | 52000 | 13000 | 20.0% | Final payment received
Sample Bathroom Addition | PRJ-2025-046 | Sarah Lee | 2025-12-01 | 2026-02-28 | Completed | 42000 | 36000 | 12500 | 14500 | 5000 | 2000 | 34000 | 8000 | 19.0% | Warranty period active
Sample Deck Construction | PRJ-2026-004 | Mike Brown | 2026-02-15 | 2026-03-30 | In Progress | 28000 | 24000 | 8500 | 9200 | 0 | 1200 | 18900 | 9100 | 32.5% | Weather delays possible
Instructions:
1. Contract Value = Total amount client agreed to pay
2. Total Budget = Your internal cost estimate (should be < Contract Value)
3. Cost Categories:
- Materials Cost: All materials | supplies | equipment rental
- Labor Cost: Wages | payroll taxes | benefits for your crew
- Subcontractor Cost: Payments to subs (plumbers | electricians | etc.)
- Other Costs: Permits | inspections | disposal | fuel | overhead allocation
4. Total Costs = sum of all cost columns
5. Gross Profit = Contract Value - Total Costs
6. Gross Margin % = (Gross Profit / Contract Value) × 100
7. Status options: Not Started | In Progress | On Hold | Completed | Cancelled
8. Update costs weekly for active projects
9. Review margins monthly to identify profitable vs problem projects
10. Use Notes for delays | change orders | issues | or milestones
KEY METRICS TO WATCH:
- Gross Margin % should be 20-35% for most projects
- If margin drops below 15% | investigate cost overruns immediately
- Track budget vs actual costs to improve future estimates